## Stargazer Rock
			Time		Status	Comments
Search for the Perfect Niche Website
	Find Niche		1 week		Done	Astronomy
	Products between $100 and $300?		1 day		Done	Yes, and well over $300
	Evergreen products?		1 day		Done	Yes, many last over 5 years
	Competition		1 day		Done	Yes, it is very competitive...

Setup Niche Website
	Find Cool Domain		1 day		Done	stargazerrock.com
	Hosting Company		0 days		n.a.	Just use existing servers
	Install Wordpress by hand		1 day		Done	This is because I do it myself, for you this is probably 1 day for deciding whether to go with Blue Host
	Finish up website setup		1 day		Done	Install various extensions (plugins)

Write Content
	Prepare Posts (search long tail keywords		3 days		Partial	This is your upfront research of what you're going to write on your Niche Website
	with Google and create a new post for each)					Add entries for each new post under the “Write Content” section below

	Write the Content
		Stargazer Definition	1 day		Done
		What's the difference between Astronomy and Astrology	3 days		Done	Take longer with a long history (this is going to be a really long page)
		Satellite Navigation—how does it work?	1 day
		Observing Satellites a New Thing Stargazers Do!	1 day
		Advice on buying a telescope online at Amazon	1 day		Done
		Why Do You Want a Case for Your Telescope?	1 day		Done
		Handheld Telescope (a.k.a. Pirate Brass Telescope with a Wooden Box)	1 day		Done